## Plan
No | Module | Description | Notes
1 | Login Page | Implement login and redirection based on user role and status. | Estimated time: 16h
2 | Register Page | User selects role during registration and waits for admin approval. | Estimated time: 16h
3 | Admin Panel - Manage Users | Admin can add/edit/delete users (students, instructors), assign roles, and track user activity. | Estimated time: 24h
4 | Admin Panel - Manage Courses | Manage course content: cover image, title, description, chapters, lessons, and tests. Assign instructors to courses. | Estimated time: 32h
5 | Admin Panel - Analytics | Track user engagement, course progress, and completion rates with performance dashboards. | Estimated time: 8h
6 | Admin Panel - System Settings | Configure system (logo, name, etc.), setup email/SMS notifications, manage roles & access. | Estimated time: 24h
7 | Student Panel - Dashboard | Displays enrolled courses and user notifications. | Estimated time: 16h
8 | Student Panel - Access Courses | Stream videos (resume from last played), download resources (with restrictions), take quizzes/tests (multi-true options). | Estimated time: 40h
9 | Student Panel - Track Progress | Show course progress, test scores, and completion percentage. | Estimated time: 8h
10 | Student Panel - Give Feedback | Submit course/instructor reviews with rating and content. | Estimated time: 16h
11 | Student Panel - Community | Discussion forums using public group chat (WebSocket-based). | Estimated time: 48h
12 | Instructor Panel - Create/Upload | Upload course material and create modules/sections. | Estimated time: 24h
13 | Instructor Panel - Course Content | Organize course modules, edit or remove lessons. | Estimated time: 8h
14 | Instructor Panel - Assign Quizzes / Homework / Exams | Create quizzes per chapter, set homework deadlines via links. | Estimated time: 16h
15 | Instructor Panel - View Students | View enrolled students and their participation/progress. | Estimated time: 8h
16 | Instructor Panel - Performance Monitoring | Monitor student progress, flag students, generate reports. | Estimated time: 16h
17 | Responsive Design | Ensure full responsive support across all modules and views. | Estimated time: 40h
18 | Integrations | Setup for video streaming APIs (Vimeo/YouTube), Firebase notifications, Google Analytics or custom tools. | No fixed estimate; depends on service.