## Basic Details
Sr No | Module Name | Section Name
1 | Dashboard | widget (Create Course, Library, Learner, group)
Counter Section
No of signup Graph (Range Wise Monthly)
(https://img001.prntscr.com/file/img001/VFWCjexmRdWMuUoYqAiByg.png)
No of signup Graph (Range Wise Monthly)
Company Lising Card With Filter (https://img001.prntscr.com/file/img001/VFWCjexmRdWMuUoYqAiByg.png)
2 | Courses | Create Course, edit, update, delete, clone, preview
2.1 | Course Overview
2.2 | Course Content
2.3 | Certification
3 | Learner | Crud Operations
3.1 | Learner Detail Screen | Edit Learner detail, deactive, delete, direct change learner, share, course direct assign, engaged collection, engaged videos, course enrollment, activity log, email log
4 | Learner Group | Crud Operations
4.1 |  | Conditional Add/Edit Learner's group,
5 | Team | Crud Operations
5.1 |  | Upload video, create folder
5.2 |  | Video Detail screen , Add thumbnail, description
https://app.trainn.co/videos/k4k0MMbOgPuVkoHdRfs2Ow/analytics
Ans |  | Delete, Move folder, anaytis
ans |  | dynamic condition on group in priporty last
ans |  | ignore manager on grp module

## Timeline
Sr.No | Module | Sub Module | Fields | Datatype | Developer Comments | Query
1 | Dashboard | 1) - Create Course - Create Learner - Create Library - Add Group 2) - Counters 3) - Number of signups Graphs with filters 4) - Top companies with filters 5) - Course Enrollment Chart with filters 6) - Top courses list with filters 7) - Unique active learners with filters 8) - Top learners with filters 9) - Total engagment time chart with filters 10) - Average rnagment time chart with filters
2 | Course | 1) Course Crud - Add - Edit - (sub module) Link - Course Analytics - filters - export - Clone - Preview - Delete 2) Chapter Crud - Rename Chapter - Reorder Chapter - Delete Chapter 3) Lesson Curd (Video Lesson) 4) Certification Crud - 5) Settings - Assessment Setting - Assessment Questionnaries | 1) Course Overview - l_id - l_course_name - l_cover_image - l_cover_video - l_short_description - l_course_description - l_internel_name - l_sequential_manner - l_certified_course - l_watch_video_to_complete_lession - Lautoplay_video - l_control_playback_video - l_comment_video_lession - l_feedback_course - l_course_authors (array) - l_active_status - i_course_active_status 2) Course Content (chapter Table) - l_id - l_course_id - l_sort_order - l_chapter_name - l_active_status 3) Course Content (Lession Table) - l_id - l_course_id - l_chapter_id - l_sort_order - l_lession_type - l_lession_content - l_lession_name - l_lession_description - l_supporting_doc_id (array) - l_active_status 4) Course Content( Lession Supporting Doc Table) - i_id - l_file - l_active_status 5) Certificate Setting Table - l_id - l_course_id - l_certificate_method - l_certificate_validity - l_cerificate_compelete_percantage - l_certifcate_name - l_name_of_autority - l_designation - l_active_status 6) Assessment Settings - l_id - l_course_id - l_without_course_completetion - l_retake_assessment - l_shuffle_question - l_minimum_score - l_numbers_of_attempts - l_reattempt_window - l_active_status 7) Assessment Questionerres Table - l_id - l_course_id - l_sort_order - l_question - l_option_type - l_options (array) - l_answer (array) - l_correct_question_marks - l_active_status |  |  | https://tinyurl.com/2yf3azfe what is use for this supporting document?
3 | Learner | 1) Learner Crud - Leaner Profile - User Engagement - Engage Video - Course Assignment - Course Entrollments - Activity Logs - Email Logs - Assign Course to learner | 8) Learners Table - l_id - l_learner_id (user_id) - i_active_status - l_account_status 9) Learner Course Progress Table - l_id 1 - l_learner_id 5 - l_course_id 5 - l_chapter_id 0 - l_mark_lession_id [20,21] - l_all_lession_id [20,21,22,23] - l_total_engagement_time [0.26] 10) Course Assignment Table - l_id - l_learner_id - l_course_id - l_sort_order - l_active_status 11) Activity Table - i_id - l_type - l_activity_log
4 | Group | - Add Learner to Group - Add Learner - Add Group - Assign Course to this | 12) Group Table - l_id - l_group_name - l_group_learners_id(array) - i_course_assignment_id - l_active_status
5 | Team | - Team - Create Team Library - Upload Video - Create Folder - Delete Folder | 13) TeamTable - l_id - l_team_type - l_team_name - l_file - l_description - l_thumbnail - l_active_status 14) Team Analytics Table - l_id - l_team_id - l_total_view - l_unqiue_view - l_like - l_dislike - l_active_status | https://tinyurl.com/2bqcue3c Need to explain how its work analytics?
6 | Settings | - Email Setting
7 | Quiz Attempts | -Quize Attempts -Verfiy learner name. -Quize Start -Quize Submit -Display Quize Result -Retake Quize | 15) quiz_attempts -l_id -l_learner_id -l_learner_name -l_quize_id -l_score -l_quize_status ['complete','in-progress'] -l_quize_attempt_answer -l_no_of_attempt -l_status
8 | Chapter wise quiz | -Quize Attempts -Add Questionnaire. -Quiz Setting -Quiz Attempt user side | 16) Chapter Quiz -l_id -l_chapter_id -l_quiz_title 17) Chapter Quiz Question -l_id -l_quiz_id -l_sort_order -l_question -l_question_marks -l_options -l_answer -l_active_status 18) Chapter Quiz Settings -l_id -l_quiz_id -is_shuffle_choices -is_shuffle_questions -is_show_quiz_attempt_summary -is_show_correct_answer_summary -l_quiz_duration -l_minimum_score -l_no_of_attempt -l_no_of_question -l_active_status 19) Chapter Quiz Attempt -l_id -l_user_id -l_quiz_id 20) User Quiz Answer -l_id -l_attempt_id -l_question_id -l_selected_option -l_is_correct -l_correct_option

## Weekly Plan
Module | Sub Module | Task | Duration | Developer
Dashboard | Section (1) ● Create Course ● Create Learner ● Create Library ● Add Group | ● Module wise attach link | 0.5 | Vandan
| Section (2) ● Counters | ● Module wise total numbers of counts add | 0.5
| Section (3.1) ● Number of signups Graphs with filters | ● Signup graph | 2
| Section (3.2) ● Top companies with filters | ● Top companies table with filter ● Companies filter ● enrollments filter | 2 | Naman
| Section (4.1) ● Course Enrollment Chart | ● Course enrollment chart | 2 | Naman
| Section (4.2) ● Top courses list with filters | ● Top courses table with filter ● enrollment filter | 2 | Naman
| Section (5.1) ● Unique active learners with filters | ● Unique acttive learners chart | 2 | Naman
| Section (5.2) ● Top learners with filters | ● Top learners with filter ● enrollment filter | 2 | Naman
| Section (6.1) ● Total engagment time chart with filters | ● Total engagment time chart | 2 | Naman
| Section (6.2) ● Average rnagment time chart with filters | ● Averge engagment time chart | 2 | Naman
| Section (7) ● Date Filter | ● Date filter add below section 2 | 1 | Naman
Module | Sub Module | Task | Duration | Developer | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-07
Course | Section (1) ● Course overview | ● Make form and add like image/video upload, description, checkboxes etc.. | 12 | Vandan | 7 | 8 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Naman | - | - | - | - | - | - | - | - | - | - | 1.5 | 2 | - | - | - | - | - | -
| Section (2) ● Course content | ● Add, Rename, reorder, delete chapter ● Add, reorder, delete lession (only video upload option) ● Upload supporting document option | 50 | Naman | 2.5 | 7.5 | 8 | 8 | 8 | 7 | - | - | - | - |  | - | - | - | 3 | 8 | - | -
| Section (3.1) ● Settings | ● Certificate settting form with option like signture upload, condition base cerficate validity | 4 | Naman | - | - | - | - | - | 1 | 3 | - | - | - | - | - | - | - | - | - | - | -
| Section (3.2) ● Assessment Setting | ● Certificate assessment setting form like number of attemps, time limit etc.. | 6 | Naman | - | - | - | - | - | - | 4 | 2 | - | - | - | - | - | - | - | - | - | -
| Section (3.3) ● Assessment Questionnaires | ● Add dynamic assessment question form with answer | 40 | Naman | - | - | - | - | - | - | 1 | 6 | 8 | 8 | 6.5 | 6 | 3 | - | - | - | - | -
| Section (4) ● Course Analytics | ● Course analytics table, filters, export etc.. | 16 | Naman | - | - | - | - | - | - | - | - | - | - | - | - | - | 2 | - | - | - | -
| Section (5) ● Course Listing | ● Course listing table with filters, clone, preview, delete | 16 | Vandan | - | - | 2 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  |  | Naman | - | - | - | - | - | - | - | - | - | - | - | - | 5 | 3 | 5 | - | - | -
|  | - | 5 | - | bar: 2024-12-11 to 2025-01-07
| Bug Resolve | - | - | Naman | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 8 | 3.5
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-08; 2024-12-12: 2025-01-13; 2024-12-13: 2025-01-15; 2024-12-16: 2025-01-16; 2024-12-17: 2025-01-17; 2024-12-18: 2025-01-20
Learner | Section (1) ● Learner Crud | ● Fetch data from partners ● Add filters, listing, delete etc.. ● Like, Dislike Functionality | 12 | Naman | 2024-12-11: -; 2024-12-12: 8; 2024-12-13: -; 2024-12-16: -; 2024-12-17: -; 2024-12-18: 4
| Section (2) ● Learner Profile | ● Basic details, edit, delete, deactive account ● User engagment ● Enagagment video ● Course assessment direct add ● Course enrollment in view attempts, re-enroll feature etc.. ● Activity log | 25 | Naman | 2024-12-11: 2; 2024-12-12: -; 2024-12-13: 8; 2024-12-16: 8; 2024-12-17: 8; 2024-12-18: -
| Buffer Time | - | 5 | bar: 2024-12-11 to 2024-12-18; 2024-12-26 to 2025-01-07
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-20; 2024-12-12: 2025-01-21; 2024-12-13: 2025-01-22
Group | Section (1) ● Group Crud | ● Create, edit, delete group with static type only ● Course assign direct ● Group listing | 20 | Naman | 2024-12-11: 4; 2024-12-12: 8; 2024-12-13: 8
| Buffer Time | - | 5 | bar: 2024-12-11 to 2024-12-13; 2024-12-26 to 2025-01-07
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-23; 2024-12-12: 2025-01-24; 2024-12-13: 2025-01-27; 2024-12-16: 2025-01-28; 2024-12-17: 2025-01-29
Team | Section (1) ● Team Crud | ● Create video or folder, delete as well ● Team data listing ● Upload video or image with description and thumbnails ● Feature like move to another folder, basic analytics | 40 | Naman | 2024-12-11: 8; 2024-12-12: 8; 2024-12-13: 8; 2024-12-16: 8; 2024-12-17: 4
| Buffer Time | - | 5 | bar: 2024-12-26 to 2025-01-07
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-21
Setting | Section (1) ● Email Setting | ● Dymamic add like subject, content, etc.. ● Email credentials form | 10 | Vandan | 2024-12-11: 6
| Buffer Time | - | 4 | bar: 2024-12-11; 2024-12-26 to 2025-01-07
Total Time |  |  | 293
Approx 300 Hours
Extra Tasks | bar: 2024-12-16
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-02; 2024-12-12: 2025-01-03; 2024-12-13: 2025-01-06
Course Frontend | Course Forntend ● Design the Course Frontend | ● Design of the Course Frontend Preview Design ● Pass Course Id to make it dynamic | 20 | Naman | 2024-12-11: 8; 2024-12-12: 8; 2024-12-13: 2
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-06; 2024-12-12: 2025-01-07
MotaData Design Bugs | Motadata design all bugs from the motadata bugs sheet Slider changes and one bug solved |  | - | Naman | 2024-12-11: 6; 2024-12-12: 4.5; 2024-12-13: -
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-08; 2024-12-12: 2025-01-09; 2024-12-13: 2025-01-10
MotaData Extra Bugs | Resolve the bugs that is givne by vandan in the other modules of the motadata |  | - | Naman | 2024-12-11: 6; 2024-12-12: 8; 2024-12-13: 6
| Dashboard Card Design |  | - | Naman | 2024-12-11: -; 2024-12-12: -; 2024-12-13: 2
Learner | Learner ● Add learner | ● Add learner with multiple select. ● Remove email and company field and display email in select user field | - | Naman | bar: 2024-12-11 to 2024-12-13
Email Setting | Email Setting | ● Change in feature add dynamic format for mail including dropdown of module and module type to show mail content body and fixed header and footer data | - | Vandan | 2024-12-11: 6; 2024-12-12: -; 2024-12-13: -
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-01-29; 2024-12-12: 2025-01-30; 2024-12-13: 31/01/2025
Dark Mode Ui changes | resolved dark mode and mono mode issue everywhere including the LMS and Motadata both the portal |  | - | Naman | 2024-12-11: 4; 2024-12-12: 4; 2024-12-13: -
| Resolved the bugs |  | - | Naman | 2024-12-11: -; 2024-12-12: 4; 2024-12-13: -
| Resolved the design bugs and the work on the team module |  | - | Naman | 2024-12-11: -; 2024-12-12: -; 2024-12-13: 8
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-02-03; 2024-12-12: 2025-02-04; 2024-12-13: 2025-02-05
Quiz Questionnaire in Frontent | Section (1) ● Make a page where user can attemp quiz and get the certificate ● Set the course wise condition based on the assesment type selected in the course | ● Create, edit, delete group with static type only ● Course assign direct ● Group listing | 18 | Naman | 2024-12-11: 8; 2024-12-12: 8; 2024-12-13: 4
| Buffer Time | - | 5 | - | bar: 2024-12-11 to 2024-12-13
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-02-05; 2024-12-12: 2025-02-06; 2024-12-13: 2025-02-07
UX Bugs | ● Solve listed task | 01. https://prnt.sc/ghq2CwCvOnoT : Make these all pages and sub-pages active if the current page is opening the same one. 02. https://prnt.sc/0fWLwcmVbG3a : This all should ne in one line. 03. https://prnt.sc/DcEVy99VHuFF : Breadcrumb is not working on any LMS pages, rest in all pages that is working : https://prnt.sc/Yj9XC9427hPY. 04. https://prnt.sc/9dkY0-5oC23F : Fix this issue. 05. https://prnt.sc/prmt1CRuSwun : LMS Dashboard spacing issue. 06. https://prnt.sc/f5Ot4KDJI536 : This is the other menu option and https://prnt.sc/bcw8HaBRjn9m this is our menu option looking bit different so check that. | - | Naman | 2024-12-11: 4; 2024-12-12: -; 2024-12-13: -
| ● Solve listed task | 07. https://prnt.sc/EWsjYaFbcMp- : This is not proper scrollable, can't able to access : https://prnt.sc/Vk-xXY6bSJR_ this 2. 08. https://prnt.sc/bd7ZVxeqiA7J : Make every popup of the LMS is with header and footer. 09. https://prnt.sc/bPasfIoaPdGv : Here we need to change this to table formate or the checkbox formate. 10. https://prnt.sc/Cv3nJkKMzm64 : We need to make this whole row clickable or make one action field and then make view button there. 11. https://prnt.sc/dc21IFZSwfNH : Quiz spelling is wrong. 12. https://prnt.sc/SAZG4vCpvWz- : Popup UI issue. | - | - | 2024-12-11: -; 2024-12-12: 8; 2024-12-13: -
| ● Solve listed task | 13. https://prnt.sc/gJUk7xldr-bw : I have created only one learner but its showing three times. 14. https://prnt.sc/LZ9Nk3QjzjCy : We need to make this whole row clickable or make one action field and then make view button there. 15. https://prnt.sc/wz-qnBG3_GPj : These buttons are not working. Make them working. 16. https://prnt.sc/4C4MUCsYRc46 : On click remove ask for the confrimation first and then perform delete option. do this for all LMS pages. 17. https://prnt.sc/dXQf9tLAVmdQ : Here also fetching the three learner and when i select once and save then also three entries are comine here : https://prnt.sc/HQgAfo2cqgHE and above cout is showing 1 only. 18. https://prnt.sc/DSRcumljo6e5 : Here we need to show the preview button to make whole row cliclable. 19. https://prnt.sc/Hbk4Te-DJsSa : Move this breadcrumb to above only. 20. https://prnt.sc/p6qX7YkfAmE4 : Successfully deleted is coming but not going from table. | - | - | 2024-12-11: -; 2024-12-12: -; 2024-12-13: 6
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-02-07; 2024-12-12: 2025-02-10; 2024-12-13: 2025-02-11; 2024-12-16: 2025-02-12
Chapter wise quiz | Add Questionnaire | ● Add quiz card ● Remove quize card ● Save answer | 12 | Naman | 2024-12-11: 2; 2024-12-12: 8; 2024-12-13: -; 2024-12-16: -
| Quiz Setting | ● Shuffle choices ●Shuffle questions ●Number of questions ●Show quiz attempt summary ●Show correct answers in the summary ●Quiz duration ●Mininum score ●Number of attempts allowed | 4 | Naman | 2024-12-11: -; 2024-12-12: -; 2024-12-13: 8; 2024-12-16: -
| Quiz Attempt user side | ● Attemp quize ● Display quiz result ● View Quiz Attempt Summary | 7 | Naman | 2024-12-11: -; 2024-12-12: -; 2024-12-13: -; 2024-12-16: 6
| Buffer Time | - | 5
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-02-12; 2024-12-12: 2025-02-13; 2024-12-13: 2025-02-14; 2024-12-16: 2025-02-17
Bugs Solving | Solve the bugs giveb by vandan | Bugs are listed in the bugs sheet | - | Naman | 2024-12-11: 2; 2024-12-12: 8; 2024-12-13: 8; 2024-12-16: -
| Improvement and Enhanacement |  | - | Naman | 2024-12-11: -; 2024-12-12: -; 2024-12-13: -; 2024-12-16: 8
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-02-18; 2024-12-12: 2025-02-19
Improvement & Enhancement | Testing whole module end to end with fresh data | Listed 18 points after fresh testing that needs to be corrected so we are solving that on 18th and 19th | - | Naman | 2024-12-11: 8; 2024-12-12: 8; 2024-12-13: -; 2024-12-16: -
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-02-21
Menu Changes | Menu chnages from horizantal to vertical as per the reference theme we used |  | 4 | Naman | 2024-12-11: 8; 2024-12-12: -; 2024-12-13: -; 2024-12-16: -
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-03-27
Dashboard | Dashboard dynamic card UI changes | drag n drop card to the also table after drag n drop we can able to move and edit that to remove card also menu sidebar for left side and right side condition | 12 | Naman | 2024-12-11: 12
Module | Sub Module | Task | Duration | Developer | 2024-12-11: 2025-04-09; 2024-12-12: 2025-04-10; 2024-12-13: 2025-04-11; 2024-12-16: 2025-04-14
Dashboard | Menu changes | drag n drop card to the also table after drag n drop we can able to move and edit that to remove card also menu sidebar for left side and right side condition | 30 | Naman | 2024-12-11: 8; 2024-12-12: 8; 2024-12-13: 8; 2024-12-16: 6

## LMS Libraries
Sr. no. | Library Name | Library Command
1 | barryvdh/laravel-dompdf | Command:-composer require barryvdh/laravel-dompdf Publish Configuration : php artisan vendor:publish --provider="Barryvdh\DomPDF\ServiceProvider"
2 | james-heinrich/getid3 | Command :-composer require james-heinrich/getid3

## LMS Bugs
Current Status | High | Medium | Low | Urgent | Immediate | Total
Done | 27 | 4 | 4 | 6 | 0 | 41
Reopen | 0 | 0 | 0 | 0 | 0 | 0
Ignore | 0 | 0 | 2 | 0 | 0 | 2
Pending | 0 | 0 | 0 | 0 | 0 | 0
Review | 0 | 0 | 0 | 0 | 0 | 0
Working | 0 | 0 | 0 | 0 | 0 | 0
Confirm | 0 | 0 | 0 | 0 | 0 | 0
Open | 0 | 0 | 0 | 0 | 0 | 0
Total | 27 | 4 | 6 | 6 | 0 | 43
Reported By | Resolved By | Layout/ Screen name | Layout size | Priority | Issue Category | Bug Description | Bug Screenshot | Reported Date | Resolved Date | Dev. Status | QA Status | Dev. Note | Dev. ScreenShot | QA Note | QA ScreenShot | Confirm By
Rajiv | Naman | Course Builder | Desktop | High | Behaviour | Common - Left Side Menu behaviour is not working correctly I means that Arrow positioning not correctly for all 3 tab menu see in train also in second when we click on then only we can see "Add Chapter" option in that right now it shows default when we are on the page. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Untitled Course Name Pop up | Desktop | High | Bug | When you try to edit first time and try to make mouse click on field then "Untitled Course Name" not blur i mean we need to select and delete and then able update name. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Overview | Desktop | Low | Bug | I think my mistake but if you see in train that image is just for cover image for video. I will explain. |  | 2024-12-30 | 2025-01-01 | Ignore | Pending | We have checked that in the trainn also its cosidering only one at time image or video
Rajiv | Naman | Course Overview | Desktop | High | Behaviour | Also In Short Description Text box when we click on than cursor also on middle of text box actually it should always on starting of textbox when its blank or first time. See Trainn anywhere of this behaviour. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Overview | Desktop | Medium | Bug | Internal Name on blur field its not Username and it should be Internal Name |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Overview | Desktop | High | Behaviour | If we upload video and all information and without save select the Author then page refresh and all information what we have added it disappear that's not correct. So on Author select we need to stop page refresh or anything so user's added information can stay and save properly. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Overview | Desktop | Low | Behaviour | When we upload Video and save then i think its taking time to save yes may be of server but make sure that it should be take reasonable speed for saving video. |  | 2024-12-30 | 2025-01-01 | Ignore | Pending | Yes we have checked in the localserver that its uploading faster then our current server
Rajiv | Naman | Course Overview | Desktop | Medium | Design | When We have add Short description and after saving it you can see content taking spacing and then started you can see AIOPS course. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Content | Desktop | Urgent | Bug | I can't able to "Add Chapter" this functionality not working please check AIOPS course i created. Please make it fix first so i can check further. |  | 2024-12-30 | 2025-01-01 | Done | Reopen | I have tested it twice but its working for me
Rajiv | Naman | Course Content | Desktop | High | Behaviour | Assessment & Certification - This menu item disable till you course save. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Content | Desktop | High | Behaviour | First of all this menu "Setting" first menu item display after saving course. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Content | Desktop | High | Behaviour | In the setting When you select "With Assessment" option from Certification Method and save this option and then only "Assessment Settings" and "Assessment Questionnaire" these two option will display in menu item. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Content | Desktop | High | Bug | When you add course name in "Course Certificate Name" then it should change in "Certification Text" in Has successfully completed the course " " |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Content | Desktop | Medium | Design | Assessment Duration When you type 30 or anything text is cutting |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Course Content | Desktop | Medium | Design | Minimum Score when you type anything text is cutting. |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Assessment Questionnaire | Desktop | Low | Behaviour | Why do have "Save" button for each question ? Actually we have select Answer and hit done i think its save no ? |  | 2024-12-30 | 2025-01-01 | Done | Pending
Rajiv | Naman | Assessment Questionnaire | Desktop | Low | Behaviour | Till hit Done why we can't able to delete? |  | 2024-12-30 | 2025-01-01 | Done | Pending
Vandan | Naman | Course,Learner,Learner Group,Email Settings module | Desktop | Low | Design | Same style button not coming. |  | 2025-01-22 | 2025-01-22 | Done | Pending
Vandan | Naman | Learner Module | Desktop | Low | Design | Add course assignment modal adding some space between course list. |  | 2025-01-22 | 2025-01-22 | Done | Pending
Vandan | Naman | Add Lesson | Desktop | High | Bug | When adding lessons through the video library, sometimes the AJAX call is made multiple times. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Assessment Questionnaire | Desktop | High | Bug | When saving question, sometimes the AJAX call is made multiple times. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Clone Course | Desktop | High | Bug | When a course is cloned and then edited, the lesson videos do not appear properly organized chapter-wise. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Assessment & Questionnaire | Desktop | High | Behaviour | When a course is created but not saved, clicking on Assessment & Questionnaires still opens it. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Assessment & Questionnaire | Desktop | High | Bug | On the settings page, the course percentage default option shows as "lifetime", but the actual percentage is displayed. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Course Overview | Desktop | High | Bug | Course Overview condition is not working. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Team Module | Desktop | High | Bug | When only a video is uploaded, it gets uploaded but does not display in the team library list. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Team Module | Desktop | High | Bug | When adding lessons through the course, the video is uploaded, but it does not display in the team library. |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Team Module | Desktop | High | Bug | When creating folder,the folder is created,but it does not display in the team library |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Team Module | Desktop | High | Bug | When creating folder,the folder is created,but it does not display in the team library |  | 2025-01-27 | 2025-01-27 | Done | Pending
Vandan | Naman | Header | Desktop | Urgent | Design | Header menu can fix according to big screen |  | 2025-02-11 |  | Done | Pending
Vandan | Naman | Every LMS Module | Desktop | High | Spelling | LMS menu category name change like All course replace with Courses change all |  | 2025-02-11 |  | Done | Pending
Vandan | Naman | Every LMS Module | Desktop | High | Spelling | All the breadscrumbs replace with for example all course to courses check all modules on lms | https://tinyurl.com/256lurle | 2025-02-11 |  | Done | Pending
Vandan | Naman | Course Analytics Page | Desktop | Urgent | Behaviour | Add count on tabs | https://tinyurl.com/2dxto28g | 2025-02-11 |  | Done | Pending
Vandan | Naman | Course Analytics Page | Desktop | High | Bug | Add dropdown instead of list of buttons on course preview section | https://tinyurl.com/22o95abv | 2025-02-11 |  | Done | Pending
Vandan | Naman | Course Edit Page | Desktop | High | Design | Main title font size decrease and sub title also | https://prnt.sc/B-cH5whVpPoY | 2025-02-11 |  | Done | Pending
Vandan | Naman | Course Edit Page | Desktop | High | Bug | hide publish button and save button replace to publish button | https://prnt.sc/sUJQ7YmP8jNy | 2025-02-11 |  | Done | Pending
Vandan | Naman | Course Assessment Questionnaire | Desktop | High | Bug | Assessment questionnarie checkboxes and radio button ui change | https://prnt.sc/Gq14uf3AJVJx | 2025-02-11 |  | Done | Pending
Vandan | Naman | Every LMS Module | Desktop | High | Design | In all forms where submit or cancel button should be as per motadata project same button apply |  | 2025-02-11 |  | Done | Pending
Vandan | Naman | Learner Details Page | Desktop | High | Design | Learner detail page add in background card apply | https://prnt.sc/wT31p6dRcbXR | 2025-02-11 |  | Done | Pending
Vandan | Naman | Learner Details Page | Desktop | High | Design | Assign course in learner detail page make good ui course listing between add some space or border so looks goood | https://prnt.sc/ycQZcqkIRtR- | 2025-02-11 |  | Done | Pending
Vandan | Naman | Learner Group | Desktop | Urgent | Bug | Learner group inside add learners, assign courses not working |  | 2025-02-11 |  | Done | Pending
Vandan | Naman | Partner Login | Desktop | Urgent | Bug | While partner login then learner should only show own courses and learners details |  | 2025-02-11 |  | Done | Pending
Vandan | Naman | Course Edit Page | Desktop | Urgent | Design | Edit course 3 dots (anyattics, delete etc.. option ) |  | 2025-02-11 |  | Done | Pending

## Motadata Bugs
Current Status | High | Medium | Low | Urgent | Immediate | Total
Done | 14 | 1 | 0 | 0 | 0 | 15
Reopen | 0 | 0 | 0 | 0 | 0 | 0
Ignore | 0 | 0 | 0 | 0 | 0 | 0
Pending | 0 | 0 | 0 | 0 | 0 | 0
Review | 0 | 0 | 0 | 0 | 0 | 0
Working | 0 | 0 | 0 | 0 | 0 | 0
Confirm | 0 | 0 | 0 | 0 | 0 | 0
Open | 0 | 0 | 0 | 0 | 0 | 0
Total | 14 | 1 | 0 | 0 | 0 | 15
Reported By | Resolved By | Layout/ Screen name | Layout size | Priority | Issue Category | Bug Description | Bug Screenshot | Reported Date | Resolved Date | Dev. Status | QA Status | Dev. Note | Dev. ScreenShot | QA Note | QA ScreenShot | Confirm By
Rajiv |  | Partner Module User Module Lead Module Collaterals Categories Collaterals SubCategories Collaterals List Mail List Event Module | Desktop | High | Design | In Action column 3 dot background same blue what we have in button or in switch right now its in grey. |  | 2025-01-06 | 2025-01-06 | Done | Done
Rajiv | Naman | Add/Edit User Add/Edit Lead | Desktop | High | Design | Can we do same size button here ? I mean make "Next" same size of "Previous" button also "Submit" too. |  | 2025-01-06 | 2025-01-06 | Done | Done
Rajiv | Naman | Add User Edit User | Desktop | High | Design | User type Switch When switch on Admin side then color should be same blue what we have in button and when select user side then color should be grey |  | 2025-01-06 | 2025-01-06 | Done | Done
Rajiv | Naman | Mail | Desktop | High | Design | "Add Mail Content" and "Add Mail Template" make same style button round and border style we have like "Add Partner" or "Add User" and make |  | 2025-01-06 | 2025-01-06 | Done | Done
Rajiv | Naman | Mail Add/Edit | Desktop | High | Design | Make all button same style we are using round and make all button same size as it looks better. |  | 2025-01-06 | 2025-01-06 | Done | Done
Rajiv | Naman | Manage Collaterals | Desktop | High | Design | Sidebar submenu Issue | https://artifexonline.slack.com/files/U045W2SLLTF/F087CK7RUSE/image.png https://artifexonline.slack.com/files/U045W2SLLTF/F087RA97XFT/image.png | 2025-01-06 | 2025-01-06 | Done | Done
Vandan | Naman | Lead Add/Edit | Desktop | High | Bug | Add and edit lead module $ and ₹ icon is not working properly | https://prnt.sc/K5sfBApZ8ush | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | Partner Module | Desktop | High | Bug | In add and edit partner somtimes the zone and region is not working | https://prnt.sc/k9WoWoY1U29R | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | User Module | Desktop | Medium | Bug | currenly after the search results are updating automatically that should not happen also make sure that search should work with name, email and company name with like query | https://prnt.sc/88MBhaBQ3Nsn | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | Zone and Region Module | Desktop | High | Bug | After updating the data select2 fields are cutting and design is breaking | https://prnt.sc/0jI2SPG_tCzP | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | Zone and Region Module | Desktop | High | Bug | When i update using this button the page is getting refreshed it should save and update information without refreshing the page | https://prnt.sc/tXDOtUSJ96kP | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | Collaterals SubCategories | Desktop | High | Bug | at the time of adding subcategories if i select the 2 document, after that the validation for the 2nd document list is missing Suggestion : we can blur the submit button until and unless all the required fields have some values | https://prnt.sc/Fr6CuGkC7dru | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | Collaterals List Collaterals Categories Collaterals SubCategories | Desktop | High | Bug | When i change the status through the switch text is not updating however its updating after refreshing the page | https://prnt.sc/B41Bbpzoi6yp | 2025-01-08 | 2025-01-08 | Done | Done
Vandan | Naman | Lead | Desktop | High | Bug | Add the info icon when multiple leads are generated for each company, and ensure the icon is added to the latest generated lead.and adding popup to display message [Partner Company Name] added this Customer Name - Customer Date - DD-MM-YYYY |  | 2025-01-09 | 2025-01-09 | Done | Done
Vandan | Naman | All Pages and sub-pages | Desktop | High | Bug | Fix the dark mode design issue in each and every page |  | 2025-01-29 | 2025-01-29 | Done | Done

## 11-02-2025 LMS Bugs
Bugs | Screenshot
Header menu can fix according to big screen
LMS menu category name change like All course replace with Courses change all
All the breadscrumbs replace with for example all course to courses check all modules on lms | https://tinyurl.com/256lurle
Add count on tabs | https://tinyurl.com/2dxto28g
add dropdown instead of list of buttons on course preview section | https://tinyurl.com/22o95abv
Main title font size decrease and sub title also | https://prnt.sc/B-cH5whVpPoY
hide publish button and save button replace to publish button | https://prnt.sc/sUJQ7YmP8jNy
Assessment questionnarie checkboxes and radio button ui change | https://prnt.sc/Gq14uf3AJVJx
in all forms where submit or cancel button should be as per motadata project same button apply
learner detail page add in background card apply | https://prnt.sc/wT31p6dRcbXR
assign course in learner detail page make good ui course listing between add some space or border so looks goood | https://prnt.sc/ycQZcqkIRtR-
learner group inside add learners, assign courses not working
while partner login then learner should only show own courses and learners details
Edit course 3 dots (anyattics, delete etc.. option )